# Board Game Reviews Blog

D05. QA WBS + Testing Phases & Activities

Project Period: 2 February 2026 - 20 April 2026

Document Deadline: 13 April 2026

Prepared by:

Test Manager & Team Lead (TM)

Test Analyst - Functional (TA)

Test Automation Engineer/SDET (TAE)

Test Environment & Technical Specialist (TE/TTA)

Version 1.0 | April 2026

1. WBS Summary

WBS ID; Work package; Output; Owner; Estimate. 1.0; QA Initiation; Test Analysis, QA Plan; TM; 3 days. 2.0; Env & Data Setup; Test Env, Seed Data, Config Docs; TE/TTA; 5 days. 3.0; Test Design; Test cases, Test Models; TA; 5 days. 4.0; Manual Execution; Executed Test Cases, Bug Reports; TA; 6-7 days. 5.0; Automation Build; Selenium Scripts, API Test Suite; TAE; 12 days. 6.0; Regression & Sign-off; Regression Report, UAT Sign-off; TM/TA; 5 days. 7.0; Reporting; Final QA Report, Lessons learned; TM; 1-2 days.

2. Phase Details

## Phase 1.0: QA Initiation

- Activities:

- Review project brief, scope, and stakeholder requirements (Code.Hub/We   Lead)

- Define QA objectives, entry/exit criteria and overall test strategy

- Identify risks and populate the initial D.11 QA Risk List

- Assign roles and responsibilities across TM, TA, TAE, TE/TTA

- Draft QA Initiation outputs: (D01,D04,D05,D06,D07,D10,D11)

- Schedule kick-off meeting and distribute QA Plan to stakeholders

- Inputs:

- Project Brief

- Requirements Specification

- Stakeholder list

- Outputs:

- D01 System Overview

- D04 QA Strategy

- D05 WBS

- D06 Resources, Costs & Time Estimation

- D07 Dependencies

- D10 Executive Summary

- D11 QA Risk List (initial version)

- High-level Roles & Responsibilities (informal/draft)

- Definition of Done:

- QA Strategy (D04) reviewed and aligned with stakeholders

- Initial Risk List (D11) baselined

- System Overview (D01) validated

- Dependencies (D07) identified and confirmed

- QA WBS (D05) approved and reflects full QA lifecycle

- Resources, Costs & Estimation (D06) validated by stakeholders

- Stakeholders agree on QA approach, scope, and governance model

- Kick-off meeting completed and formally documented

## Phase 2.0: Environment & Data Setup

- Activities:

- Install and configure WampServer (local test environment) and verify connectivity

- Deploy the Board Game Reviews Blog application to the test environment

- Set up and validate database schema and initial configuration

- Create and validate seed data (users, board games, reviews, categories)

- Configure Asana project for defect tracking and test management

- Document environment configuration, dependencies and rollback procedures

- Execute environment smoke test to confirm readiness

- Inputs:

- Application build

- WampServer installer/runtime packages

- Database schema

- Deployment instructions (if available)

- Asana project access

- Outputs:

- Environment operational

- Seed data scripts/dataset

- Environment Setup Report (D07-updated/refined)

- Initial Dependency Log (D07)

- Asana project configured for QA execution

- Definition of Done:

- Environment smoke test passed with 0 critical defects

- Application deployed successfully and accessible

- Seed data loaded and validated successfully

- Asana project fully operational for defect tracking

- Environment configuration documented and approved

- No blocking dependencies for QA execution identified

## Phase 3.0: Test Design

- Activities:

- Analyse functional requirements and user stories (D01, D02, D03)

- Create user flow diagrams for core journeys: login, search, comment, post creation, user management

- Design manual test cases for all functional areas (login, blog posts, reviews, search)

- Establish Requirements Traceability Matrix (RTM) linking requirements to test cases

- Define test data requirements in collaboration with TE/TTA

- Review and baseline test cases with TM before execution

- Inputs:

- Requirements Specification (D01)

- System Overview (supporting input)

- Test Models/Wireframes (D02/D03)

- Seed Data (from Environment phase)

- QA Strategy (D04)

- Outputs:

- Manual Test Case Suite

- Requirements Traceability Matrix (RTM)

- Test Data Requirements Specification

- User Flow Diagrams (core journeys)

- Definition of Done:

- 100% of in-scope requirements are covered by at least one test case

- Requirements Traceability Matrix reviewed and approved by TM

- Test cases reviewed, consistent and baselined

- User flows validated for all critical journeys

- Test data requirements agreed with TE/TTA

## Phase 4.0: Manual Execution

- Activities:

- Execute all manual test cases against the test environment

- Record actual results and compare them against expected results

- Log defects in Asana including severity, priority, steps to reproduce, evidence (screenshots/logs)

- Perform exploratory testing on high-risk user flows (login, review submission, search, post creation)

- Re-test fixed defects and perform regression checks where applicable

- Update defect status in Asana (Open → In Progress → Fixed → Verified/Closed)

- Provide daily execution status updates to TM

- Inputs:

- Manual Test Case Suite

- Requirements Traceability Matrix (RTM)

- Configured Test Environment

- Seed Data

- Asana access (project + workflows)

- Test Data Specifications

- Outputs:

- Executed Test Case Results (Pass/Fail/Blocked)

- Defect Reports in Asana (with full lifecycle tracking)

- Daily Execution Status Reports

- Regression/Re-test results log

- Definition of Done:

- 100% of planned test cases executed or properly marked as Blocked

- All Critical and High severity defects are resolved and verified

- Defect closure rate ≥ 90% (excluding deferred/known issues)

- Regression testing completed for all fixed defects

- Test execution report reviewed and accepted by TM

## Phase 5.0: Automation Build

- Activities:

- Define automation strategy: scope, tools (Selenium + Java), framework architecture and conventions

- Set up automation framework (project structure, Page Object Model, reporting, utilities, test data handling)

- Implement UI automated test scripts for critical flows: Login, CRUD operations, core user journeys

- Implement API automated test scripts for backend endpoints using Java REST libraries

- Integrate automated tests with CI pipeline and configure execution + reporting (local or CI environment)

- Peer-review automation scripts with TA and refactor flaky/stable tests for reliability

- Maintain and optimize test stability (reduce flakiness, improve waits, retries, assertions)

- Inputs:

- Manual Test Case Suite

- Requirements Traceability Matrix (RTM)

- API Documentation/Swagger/Postman collection

- Automation Strategy (D04-QA Strategy reference)

- Stable Test Environment

- Test Data Specifications

- Outputs:

- Selenium UI Automation Test Suite

- API Automation Test Suite

- CI Integrated Automation Pipeline

- Automation Execution Reports (CI runs)

- Automation Framework Documentation (structure, standards, setup guide)

- Definition of Done:

- Automation suite covers ≥ 80% of critical business paths

- Pass rate ≥ 95% across 3 consecutive stable runs in CI

- All scripts are committed to version control repository

- No high-severity flaky tests remaining (flakiness controlled/isolated)

- CI pipeline successfully triggers and executes automation tests

- Framework documentation completed and reviewed

## Phase 6.0: Regression & Sign-off

- Activities:

- Execute full regression test suite (manual + automated)

- Verify that all previously logged Critical/High severity defects are resolved and re-tested

- Coordinate and support User Acceptance Testing (UAT) sessions with Code.Hub/We Lead stakeholders

- Collect, document and validate UAT feedback and results

- Confirm all exit criteria are met (coverage, defect status, execution completion)

- Escalate any blocking issues to TM and project stakeholders

- Prepare final QA sign-off package and obtain formal stakeholder approval

- Inputs:

- Release Candidate (RC) build

- Regression test suite (manual + automated)

- Defect log from execution phase

- UAT test scenarios and acceptance criteria

- RTM (Requirements Traceability Matrix)

- Outputs:

- Regression Test Report

- UAT Results Report

- Final Defect Status Report

- QA Sign-off Document

- Updated Requirements Traceability Matrix (final coverage confirmation)

- Definition of Done:

- 100% of regression test suite executed

- All Critical and High severity defects are closed and verified

- No blocking issues remaining for release

- Formal UAT sign-off received from stakeholders

- All exit criteria fully met and documented

- QA sign-off approved by TM and stakeholders

## Phase 7.0: Reporting

- Activities:

- Consolidate all test execution results, defect metrics, automation results and coverage data

- Produce Final QA Report including: scope summary, execution summary, metrics, defect analysis and test coverage

- Document Lessons Learned and process improvement recommendations

- Archive all QA artefacts (test cases, scripts, reports, RTM, logs) in shared repository

- Present Final QA Report to Code.Hub/We Lead stakeholders

- Perform formal QA closure and confirm project QA completion

- Inputs:

- All execution reports (manual + automated)

- Defect log (Asana)

- UAT Sign-off document

- Regression & automation reports

- RTM (final version)

- Existing Risk Register (D11) + risk tracking updates

- Outputs:

- Final QA Report (D10-Executive Summary/QA Closure Report)

- Risk Management Plan (D12-finalized version)

- Archived QA Artefacts Repository (test cases, scripts, logs, reports, RTM)

- Final QA Metrics Dashboard (coverage, defects, execution stats)

- Definition of Done:

- Final QA Report reviewed and formally accepted by stakeholders

- Risk Management Plan (D12) finalized and agreed

- 100% of QA artefacts archived in repository

- No open QA activities remaining

- Formal QA phase closure confirmed by Code.Hub/We Lead

- All metrics validated and consistent across sources