## WBS
Board Game Reviews Blog - QA WBS with durations and dependencies
WBS ID | QA Activity | Depends On | Duration | Outputs
1 | QA Initiation | Project Brief, Requirements | 3 days | Test Analysis, QA Plan (D01,D04,D05,D06,D07,D10,D11)
2 | Env & Data Setup | D01 | 5 days | Test Env, Seed Data, Config Docs (D07), Smoke Test Results
3 | Test design | D01, D02, D03, D04 | 5 days | Test Cases, Test Models (D02,D03), Test Data Requirements
4 | Manual Execution | Test Cases, Env readiness | 6-7 days | Executed Test Cases, Bug Reports (Asana)
5 | Automation Build | D04, Stable env | 12 days | Automation Suite( Selenium scripts, API Test Suite)
6 | Regression & Sign-off | Execution, Automation Suite | 5 days | Regression Report, UAT Report, Final Defect Status, Sign-off Document
7 | Reporting | All reports/UAT Sign-off | 1-2 days | D10, D12, Archived QA Assets

## Times
Board Game Reviews Blog - QA WBS and dependencies and earliest timing
Start date: 2 February | End date: 20 April | Total: 78 working days
WBS ID | QA Activity | Depends On | Duration | Start | End
1 | QA Initation | Project Brief, Requirements | 3 days | Day 1 | Day 3
2 | Environment setup | D01 | 5 days | Day 1 | Day 6
3 | Test design | D01,D02,D03,D04 | 5 days | Day 6 | Day 11
4 | Manual Execution | Test Cases, Env readiness | 6-7 days | Day 12 | Day 19
5 | Automation build | D04, Stable env | 12 days | Day 20 | Day 32
6 | Regression & Sign-off | Execution, Automation Suite | 5 days | Day 33 | Day 38
7 | Reporting | All reports/UAT Sign-off | 1-2 days | Day 39 | Day 41
- | Buffer / Contingency | - | 19 days | Day 42 | Day 78