## Estimates
Estimates |  |  |  |  | Assumptions
Test Manager & Team Lead (TM): 35€ per hour
QA Activity | Role | Effort | Rate | Cost | Test Analyst - Functional (TA): 18€ per hour
QA Initiation | TM | 72 hours | 35 | 2520 | Test Automation Engineer / SDET (TAE): 30€ per hour
Env & Data Setup | TΕ/ΤΤΑ | 120 hours | 28 | 3360 | Test Environment & Technical Specialist (TE/TTA): 28€ per hour
Test Design | TA | 120 hours | 18 | 2160
Manual Execution | TA | 144-168 hours | 18 | 2592-3024€ | Totals
Automation Build | TAE | 288 hours | 30 | 8640 | Total effort: 936 hours
Regression & Sign-off | TM/TA | 120 hours | 35/18€ | 4,200/2,160€ | Total cost: 23,544€
Reporting | TM | 24-48 hours | 35 | 840/1,680€