D07. Dependency Analysis (Critical Path)

## Dependency list

| ID | Dependency | Depends on | Impact if delayed | Owner |
| --- | --- | --- | --- | --- |
| DEP01 | Sync of Media (Uploads) & Database (SQL) | All team members | Broken images on individual screens. Inability to verify the "Board Games Reviews" design. | TM/TE/TTA |
| DEP02 | WampServer/local Environment setup | TE/TTA (per team member) | Team members cannot execute any local test cases. Entire Phase 2 (Environment Setup) is blocked. | TE/TTA |
| DEP03 | Database (SQL) import | TE/TTA/all team members | Without test data (users, posts, etc.), functional testing cannot be performed. | TE/TTA |
| DEP04 | Staging & production access | TM/Developer | Without access, regression testing and UAT cannot be executed, only local testing is possible. | TM |
| DEP05 | REST API Availability (users endpoint) | Developer/TE/TTA | If unavailable, API testing and automation cannot be performed. | TAE/TE/TTA |
| DEP06 | Role-based test data (Admin, Author, Subscriber) | TE/TTA | Without these roles, permission (RBAC) testing cannot be executed. | TE/TTA |
| DEP07 | WordPress plugins (Basic Auth, SwaggerUI) | Developer/TE/TTA | If missing, API testing cannot be performed. | TE/TTA/Dev |

## Mitigation/Workaround

- DEP01

If media sync is delayed:

- Step 1: TE/TTA zips the folder C:\wamp64\www\wordpressTestSite\wp-content\uploads.

- Step 2: Share the zip file with the team via OneDrive/Google Drive.

- Step 3: Each member must unzip it in their local WordPress directory.

- Temporary Action: Proceed with functional testing of texts/links and ignore missing images until sync is complete.

Fallback: If sync is still delayed after Day 3, TM escalates to Code.Hub/We Lead and adjusts Phase 2 end date.

- DEP02

If WampServer setup is delayed:

- Step 1: TE/TTA provides a clear setup guide (WampServer version, PHP settings, Virtual Host config).

- Step 2: Setup must be completed and verified before Day 1 ends.

- Step 3: TE/TTA performs a remote verification session and provides remote support if needed.

Fallback: If WampServer setup fails, team members use a shared remote Dev environment provisioned by TE/TTA.

- DEP03

If database import is delayed:

- Step 1: TE/TTA exports the .sql file and shares it with the media zip.

- Step 2: Each member imports it via phpMyAdmin.

- Step 3: TE/TTA runs a quick DB integrity check (OPTIMIZE TABLE) after each import.

- Temporary Action: Use minimal or dummy data for testing.

Fallback: If the database import fails, the TE/TTA provides a simple seed data script with basic data so Phase 3 (Test Design) can continue normally.

- DEP04

If Staging/Production access is delayed:

- Step 1: TM requests and confirms access for the entire team

- Step 2: Follow up with stakeholders if access is not granted.

- Temporary Action: Continue testing in the local Dev environment.

Fallback: Regression limited to local Dev environment.

- DEP05

If REST API is unavailable:

- Step 1: TE/TTA verifies the /users’ endpoint via Postman

- Step 2: Ensure Basic Auth plugin is enabled.

- Step 3: TAE keeps API tests isolated so they can be skipped without blocking the UI suite

- Temporary Action: Skip API tests and continue with UI testing.

Fallback: Mark API tests as “blocked” in Asana and proceed with automation on UI.

- DEP06

If role-based test data is missing:

- Step 1: TE/TTA creates and verify 4 test accounts (Admin, Author, Subscriber, Visitor).

- Step 2: Accounts are documented with credentials in a secure test data sheet.

- Step 3: Include them in the database export.

Fallback: TE/TTA creates accounts manually on the local Dev environment if DB import is delayed.

- DEP07

If WordPress plugins are unavailable:

- Step 1: TE/TTA verifies both plugins (Basic Auth, WP API Swagger UI) are installed and active.

- Step 2: Plugin versions are frozen (no updates during testing).

- Temporary Action: Skip API-related testing.

Fallback: If a plugin is missing, Dev installs it immediately. If unavailable, log the issue and mark related test cases as blocked in Asana.

## 3. Critical path impact

The following dependencies are on the critical path and if delayed, they directly push out the project end date (Day 78/20 April 2026):

- DEP01: Media sync must be resolved by Day 3, or Phase 3 Test Design is compromised.

- DEP02: WampServer must be resolved by Day 1, or Phase 2 is entirely blocked.

- DEP03: Database import must be resolved by Day 5, or Phase 4 Manual execution cannot start.

- DEP04: Staging/Production Access must be resolved by Day 24 or Phase 6 Regression & Sign-off cannot be executed in a valid environment.

- DEP06: Role-based test data must be resolved by Day 5 or all RBAC test cases are blocked.

- Non-critical path (can be resolved in parallel without delaying the overall schedule): DEP05, DEP07.