## Sheet1
| Deliverable | Lead | Support | Target Date | Based on Bootcamp Module
1 | D01 System Overview | Ανδρονίκη | Κατερίνα, Ευαγγελία | 30/03 | ISTQB Foundations 1-2
2 | D02 Test Wireframes | Κατερινα |  | 30/03 | ISTQB Foundations 2
3 | D03 Test Models | Κατερινα | Ευαγελία, Ανδρονίκη | 31/03 | ISTQB Foundations 2 (T.Design)
4 | D04 QA Strategy | Κατερινα | Ανδρονίκη | 31/03 | JAVA, xUnit, Postman
5 | D05 QA WBS | Ευαγγελία |  | 2026-01-04 | ISTQB Foundations 4 (Management)
6 | D06 Resources Costs | Ευαγγελία |  | 2026-01-04 | ISTQB Foundations 4 (Mgmt)
7 | D07 Dependency | Ευαγγελία | Ανδρονίκη | 2026-02-04 | ISTQB Foundations 4 (Mgmt)
8 | D08 QA GANTT | Ελλή | Ανδρονίκη | 2026-02-04 | ISTQB Foundations 4 (Mgmt)
9 | D09 Resource RACI | Ελλή |  | 2026-03-04 | ISTQB Foundations 4 (Mgmt)
10 | D11 QA Risk List | Ελλή/Ανδρονίκη |  | 2026-03-04 | ISTQB Foundations 5 (Risk)
11 | D12 Risk Mgmt Plan | Ανδρονίκη |  | 2026-04-04 | ISTQB Foundations 5 (Risk)
12 | D10 Exec Summary | Ευαγγελία/Ελλη |  | 2026-04-04
Test Manager & Team Lead (TM)
Focus: Test Planning, WBS, Costs, GANTT, Risks, Executive Summary.
Deliverables (Lead): D01, D05, D06, D08, D10, D11, D12.
Strategy: Διαχείριση ρίσκων και επικοινωνία με stakeholders (CodeHub/We Lead).
Test Analyst - Functional (TA)
Focus: Requirements Analysis, System Overview, Wireframes, Test Models.
Deliverables (Lead): D02, D03.
Strategy: Οπτικοποίηση user flows (αναζήτηση, κριτικές) και manual test case design.
Test Automation Engineer / SDET (TAE)
Focus: Automation Strategy, Selenium (UI), Java/REST (API), Framework Maintenance.
Deliverables (Lead): D04, Test Scripts, Automation Execution.
Strategy: Διασφάλιση αξιοπιστίας των κρίσιμων scripts (Login, CRUD operations).
Test Environment & Technical Specialist (TE/TTA)
Focus: Infrastructure (WampServer), Seed Data, Resource Matrix, Dependency Analysis.
Deliverables (Lead): D07, D09, Environment Setup, Bug Reports (Jira).
Strategy: Προετοιμασία δεδομένων δοκιμής και τεχνική αρχιτεκτονική περιβάλλοντος.